## Sheet1
Electroscan, Inc. |  |  | 20 In-Store Scanner Project
555 Alcorn Street, Suite 5 |  |  | (thousands of dollars)
Boston, Massachusetts |  |  | Actual Progress a/o January 1
NAME | PV | EV | AC | SV | CV | BAC | EAC
Scanner Project | 420 | 395 | 476 | -25 | -81 | 915 | 1128
H 1.0 Hardware | 92 | 88 | 72 | -4 | 16 | 260 | 243
H 1.1 Hardware Specifications (DS) | 20 | 20 | 15 | 0 | 5 | 20 | 15
H 1.2 Hardware Design (DS) | 30 | 30 | 25 | 0 | 5 | 30 | 25
H 1.3 Hardware Documentation (DOC) | 10 | 6 | 5 | -4 | 1 | 10 | 8
H 1.4 Prototype (PD) | 2 | 2 | 2 | 0 | 0 | 40 | 40
H 1.5 Test Prototypes (T) | 0 | 0 | 0 | 0 | 0 | 30 | 30
H 1.6 Order Circuit Boards (PD) | 30 | 30 | 25 | 0 | 5 | 30 | 25
H 1.7 Preproduction Models (PD) | 0 | 0 | 0 | 0 | 0 | 100 | 100
OP 1.0 Operating System | 195 | 150 | 196 | -45 | -46 | 330 | 480
OP 1.1 Kernel Specifications (DS) | 20 | 20 | 15 | 0 | 5 | 20 | 15
OP 1.2 Drivers | 45 | 55 | 76 | 10 | -21 | 70 | 97
OP 1.2.1 Disk Drivers (DEV) | 25 | 30 | 45 | 5 | -15 | 40 | 60
OP 1.2.2 I/O Drivers (DEV) | 20 | 25 | 31 | 5 | -6 | 30 | 37
OP 1.3 Code Software | 130 | 75 | 105 | -55 | -30 | 240 | 368
OP 1.3.1 Code Software ( C ) | 30 | 20 | 40 | -10 | -20 | 100 | 200
OP 1.3.2 Document Software (DOC) | 45 | 30 | 25 | -15 | 5 | 50 | 42
OP 1.3.3 Code Interfaces ( C ) | 55 | 25 | 40 | -30 | -15 | 60 | 96
OP 1.3.4 Beta-Test Software (T) | 0 | 0 | 0 | 0 | 0 | 30 | 30
U 1.0 Utilities | 87 | 108 | 148 | 21 | -40 | 200 | 260
U 1.1 Utilities Specifications (DS) | 20 | 20 | 15 | 0 | 5 | 20 | 15
U 1.2 Routine Utilities (DEV) | 20 | 20 | 35 | 0 | -15 | 20 | 35
U 1.3 Complex Utilities (DEV) | 30 | 60 | 90 | 30 | -30 | 100 | 150
U 1.4 Utilities Documentation (DOC) | 17 | 8 | 8 | -9 | 0 | 20 | 20
U 1.5 Beta-Test Utilities (T) | 0 | 0 | 0 | 0 | 0 | 40 | 40
S 1.0 System Integration | 46 | 49 | 60 | 3 | -11 | 125 | 145
S 1.1 Architecture Decisions (DS) | 9 | 9 | 7 | 0 | 2 | 10 | 8
S 1.2 Integration Hard/Soft (DEV) | 25 | 30 | 45 | 5 | -15 | 50 | 75
S 1.3 System Hardware/Software Test (T) | 0 | 0 | 0 | 0 | 0 | 20 | 20
S 1.4 Project Documentation (D)C | 12 | 10 | 8 | -2 | 2 | 15 | 12
S 1.5 Integration Acceptance Testing (T) | 0 | 0 | 0 | 0 | 0 | 30 | 30
Note: There are minor errors in the Larson & Gray (2013) table. These appear to be found only in the EAC column. They are corrected here.
You have been serving as Electroscan’s project manager and are now well along in the project. Develop a narrative status report for the board of directors of the chain store that discusses the status of the project to date and at completion. Be as specific as you can using numbers given and those you might develop. Remember, your audience is not familiar with the jargon used by project managers and computer software personnel; therefore, some explanation may be necessary. Your report will be evaluated on your detailed use of the data, your total perspective of the current status and future status of the project, and your recommended changes (if any).

## EVM Calculations
Planned Value (PV)
PV = Percent Complete (planned) x Task Budget
$420, 000
Budget at Completion (BAC)
BAC = Project Budget
(420 000/ 925 000) x 100%
45.4%
Estimate at Completion (EAC)
EAC = BAC/CPI | or EAC = AC + (BAC – EV)
395 000/925 000 x100%
42.7%
Scheduled Variance (SV)
SV = EV – PV
EV= 395, 000
PV= 420,000
SV= -25,000 | from the SV, it is possible to derive the schedule delay which in this case is a negative figure indicating that the project is behind schedule